Project Management: Constructing a Tidal Power Plant in Saint Martin

You have recently appointed as a project manager to make a feasibility study to test a tidal type electric power generation in Saint-Martin Island.  You have prepared list of activities and estimated duration time, which shows as follows

| Activity code | Duration (week) | Predecessor Activity (code) |
| --- | --- | --- |
| A | 2 | - |
| B | 3 | - |
| C | 5 | A |
| D | 5 | A |
| E | 6 | B |
| F | 1 | B |
| G | 4 | B |
| H | 5 | C |
| I | 3 | C,D |
| J | 2 | E,F |
| K | 4 | H,I,J |
| L | 2 | J,G |
| M | 5 | K,L |

- Calculate how many minimum weeks it will require to complete the project

- What will be the slack time of each activities

- Due to resource constraint, your manager notified you that activities D, F and G can will only have 50% of resources (i.e. duration time will be doubled). Will it make the project any delay?

- By completing the project on due time (21 weeks), the company will receive an award from project sponsors´ of 5,00,000 BDT. If you feel that project will be delayed due to 50% pace of activities D, F and G you have alternate option to hire additional workers from a third party. By hiring additional resources for activities D, F and G to complete in due time it will cost 50,000 BDT each week for each activities.  What will be the minimum additional cost you could allocate to hire resources from third party?

Solution

Available paths:

Paths			Duration (weeks)

A-C-H-K-M		21 (Maximum), Critical path

A-C-I-K-M		19

A-D-I-K-M		19

B-E-J-L-M		18

B-F-J-L-M		13

B-E-J-K-M		20

B-F-J-K-M		20

B-G-L-M		14

Here, duration for A-C-H-K-M is maximum, which is the critical path. So, the project will require minimum 21 weeks to complete.

Slack time

Alternate way

Notes: Standard symbol

Slack time = Early start- Late Start

- Here, the duration time for D, F and G would be 10, 2 and 8 weeks respectively. So, from previous scenario, the duration time for activities D, F and G would be increased by 5, 1 and 4 weeks respectively. The slack time for D, F and G is 2, 6 and 7 weeks. So, the increased duration for F (1)and G (4) is less than their slack time. So it will not change the completion time of the project.

However, for activity D, slack time is 2 weeks and duration time will be increased by 5 weeks, which is greater than slack time. So, project will be delayed by (5-2)= 3 weeks due to increased duration of activity D.

Sample proof (D, F and G would be increased by 5, 1 and 4)

A-C-H-K-M		21

A-C-I-K-M		19

A-D-I-K-M		19 +5 = 24

B-E-J-L-M		18

B-F-J-L-M		13 + 1 = 14

B-E-J-K-M		20

B-F-J-K-M		20 +1 = 21

B-G-L-M		14 +4 = 18

- As the activity, D is the main constraint that will delay the completion time of the project, we need to hire additional resource for activity D only. As, activity D has already 2 weeks of slack time, we need to hire resource for 3 weeks only. In such case, amount need to be paid by (3 x 50,000) = 1,50,000 BDT to hire additional resource.  By investing 1,50,000 BDT company can still gain (5,00,000 – 1,50,000) = 3,50,000 BDT of extra profit by completing the project within 21 weeks.